## Risk-Issues
High Risk
Med Risk | Project - Issues and Risks | [6 empty] | DashBoard?
Low Risk | Item # | Issue/Risk | Description | Resolution Plan / Mitigation Plan | Contingency Plan | Due Date | Owner
| R-7 | Risk | COVID-19 causes budget cuts & project shortages in client organization, which may cause a shutdown of the project. | 1) Set up meeting with client to discuss project milestone payments | 1) Close the project | Payment collection day | Project Manager | Y
| R-3 | Risk | Defect fixing task may take longer than expected because of insufficient code coverage, which will delay the testing phase schedule. | 1) Perform defect testing earlier on in the schedule 2) Monitor the development process frequently to prevent defect situations | 1) Formulate a defect fixing plan | 2020-11-30 | Shweta | N
| R-6 | Risk | When deploying the website, the server might crash, delaying our scheduled deployment time. | 1) Daily measurement of network requirement before deployment 2) Set up a backup server to prevent server issue | 1) Set up a backup server to prevent server issue 2) Take precautionary measures for network failures | 2021-01-15 | Nisha | Y
| R-9 | Risk | As a result of COVID-19, all employees are forced to work from home, which may lead to meetings taking longer than before. Each employee may have different network speed, using VPN and VM is slower than usual, which may reduce the efficiency | 1) Using a good video conferencing software to improve working efficiency 2) Traing IT department to fix the network issue. | 1) Mandate weekend work to remian on schedule 2) Have frequent conference meetings | ASAP
| R-10 | Risk | The end-to-end testing may not complete as per schedule due to lack of code coverage for front-end | 1) Testing team should create more test cases in order to give a better code coverage 2) Perform partial end-to-end testing before schedule | 1) Keep track of testing and hire experts to solve this issue | 2020-12-29
Project Manager
Project - Issues and Risks -- CLOSED
| Item # | Issue/Risk | Description | Resolution Plan / Mitigation Plan | Close Reason | Date Closed | Closed By
| R-1 | Risk | Requirements Draft document might be delayed if Customer Interviews are not held per schedule. | 1) PM to review schedule with customer to set up new interview appointment 2) Prepare all interview questiones and documents prior interview to improve interview quality | 1) This risk does not happen, all requirement document are signed off on time. | 2020-07-24 | PM
| R-2 | Risk | Developer1 may have schedule conflict due to another project commitment, which would delay the server setup development task. | 1) Determine if we can delay server development without impact critical path 2) Development team leader need to ensure development progress on schedule 3) Create vacation schedule, request all team member follow schedule | Development team lead arrage another developer to make up developer 1's task, server up progress was on time | 2020-08-21 | PM
| R-5 | Risk | User interface design may not meet the requirement document due to additional scope change, since clients changed their mind | 1) PM should communicate with client and make sure they follow the requirement document | 1) Deisgn team leaders should require designers to follow requirement document | 2020-07-24 | PM
| R-4 | Risk | Developer 3 may have difficulty in finishing the implementation of the code navigation system function on time due to the map API usage lackage. | 1) Find Subject Matter Expert in company that can help 2) Bring external resources to help finish on time 3) Start designing alternate solutions | The senior developer joined in and help with this issue, the challenge is resolved. | 2020-09-27 | PM
| R-8 | Risk | The testing progress for user profile history function and auto parts info list function may not be finish on time, since the implementation of these two function took longer. | 1) Tester 1 have slack at this moments, he can join in and help pushing the progress | 1) Keep track of testing and hire experts to solve this issue | 2020-10-06 | Testing Lead
| I-1 | Issue | COVID-19 forces everyone to keep social distance, Customer interview has to be held online, planned schedule is not followed, interview quality is low, schedule is delayed. | 1) Contact customer to set up a new interview appointment. 2) Inform customers that we will record every meeting to | N/A - already in resolution mode | 2020-07-29 | Project Manager

## Action Item
Project Action List
# | Description | Originator | Owner | Date Assigned | Date Needed | Date Closed | Comments | Status
A-13 | Delopyment team should moniter the website admin and server admin connection qualities | Project Manager | Deployment Lead | 2020-10-05 | 2021-01-01 |  | Make sure when deploy the website, the server and website admin are working functional | In progress
A-15 | Testing team, design team and development team and deployment team leaders should have a meeting to go over the entire project. | Project Manager | Project Manager, all team leads | 2020-10-02 | 2021-01-08 |  | To ensure that deployment is 100% successful. | In progress
A-16 | Testing Team to complete front-end testing to stay on schedule | Project Manager | Testing Team Lead | 2020-11-26 | 2020-12-17 |  | To ensure deployment is not delayed | In progress
A-17 | Testing Team to finish end-to-end testing (including database, server, front-end, back-end) | Project Manager | Testing Team Lead | 2020-11-26 | 2020-12-29 |  | To ensure we have all components functioning according to the requirements | In progress
A-18 | Deployment Team should hand-off the project and collect customer reviews and sign-off after successful deployment | Project Manager | Deployment Lead | 2020-11-26 | 2021-01-20 |  | To ensure customer is satisfied with the delivered project | In progress
A-19 | Project Manager should close the project by providing post-completion support plan, disaster recovery plan and client training plan | Project Manager | Project Manager | 2020-11-25 | 2021-01-25 |  | To make sure project is closed before we could move on to a new project | In progress
A-20 | Accountant should collect all the project payments | Project Manager | Accountant | 2020-07-31 | 2021-01-25 |  | To keep a track of amount spent and profit margin | In progress
A-21 | Project Manager should perform project audit and draft lessons learned document for future project references | Project Manager | Project Manager | 2020-11-25 | 2021-02-10 |  | To have future references for similar projects | In progress
CLOSED ACTION ITEMS
A-1 | Requirements Lead will send idea Interview Schedule to PM to review with customer. | James | Requirements Lead | 2020-06-18 | 2020-06-24 | 2020-06-25 | Requirements Lead will review Project Schedule and finalize plan with Requirements Team | Finished
A-2 | Setup meeting with Customer to review Interview Schedule to meet with Requirements Engineers. | James | Project Manager | 2020-06-25 | 2020-07-02 | 2020-07-03 | Will setup meeting with customer based on customers schedule and plan from Requirements Team | Finished
A-3 | Setup meeting with Customer to review draft requirement documents | Shweta | Project Manager | 2020-07-03 | 2020-07-04 | 2020-07-05 | Will setup meeting with customer to review req document | Finished
A-4 | Review draft requirement documents with requirement team lead | Shweta | Requirements Lead | 2020-07-05 | 2020-07-07 | 2020-07-08 | Will setup meeting with requirement team lead to review req document | Finished
A-5 | Review design plan with disgn team lead based requirement document | Nisha | Design team lead | 2020-07-08 | 2020-07-09 | 2020-07-10 | Will setup meeting with design team lead to review req document | Finished
A-6 | Review test case with test team lead | Nisha | Test team lead | 2020-07-10 | 2020-07-13 | 2020-07-14 | Will setup meeting with test team lead to review req document | Finished
A-7 | Setup meeting with Customer to review revised requirement documents, design plan, test cases. | James | Project Manager | 2020-07-14 | 2020-07-17 | 2020-07-18 | Will setup meeting with customer to review final req document | Finished
A- | Email customer to send back signed LOA for reg document | James | Project Manager | 2020-07-18 | 2020-07-23 | 2020-07-24 | Contact James before set up the meeting | Finished
A-17 | Host two standup meetings to mitigate the COVID-19 work from home situation | Shweta | Project Maanager | 2020-09-25 | 2020-09-28 | 2020-09-28 | This will help better progress tracking | Finished
A-9 | Set up front-end testing environment to preprare front-end testing process | Project Manager | Testing lead | 2020-10-02 | 2020-11-04 | 2020-11-05 | Set up early to speed up the testing phase | Finished
A-10 | Set up back-end testing environment to preprare back-end testing process | Project Manager | Testing lead | 2020-10-02 | 2020-11-07 | 2020-11-09 | Set up early to speed up the testing phase | Finished
A-11 | Set up a demo meeting with design team and developer team for server testing result | Testing lead | Project Manager | 2020-10-05 | 2020-10-08 | 2020-10-09 | Make sure all testing procedure are follow the design and requirements | Finished
A-12 | Tester 1 should collaberate with tester 2 on database function test | Testing lead | Tester 1 | 2020-10-02 | 2020-10-06 | 2020-10-07 | The project is behind of schedule, need to push the progress | Finished
A-14 | We finished 50% project ontime, give project team a day break on Friday 10/9/20 | Project Manager | Project Manager | 2020-10-05 | 2021-10-08 | 2020-10-09 | To acknowledge and appreciate all the efforts the team has put into the project | Finished

## Decisions
Project Decision List
# | Description | Owner | Date | Comments
D-1 | Project team decides to meet every day 9:30 am to monitor the project progress | PM | 2020-06-30 | Everyone is WFH, should keep track of project schdule
D-2 | Design team decides to use AWS as the server | Design team leader | 2020-08-03 | Use AWS as server platform
D-3 | Decide to have monthly meeting with the leadership to report project progress | PM | 2020-07-03 | Leader team wants to know the project progress
D-4 | Deployment team leader decides to have stand up meeting everyone with development meeting to exchange information | Deployment Lead | 2020-07-03 | Keep each team on the same page
D-5 | Projevct Manager Decide to meet with the Accountant and ensure that all payment milestones have been collected | PM | 2020-11-18 | To ensure we are paid timely
D-6 | Testing team decides to meet with the requirements tem to ensure all compnents are functioning as per requirements | Testing TEam Lead | 2020-09-24 | To ensure extensive functionality of the delivered project